## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 1426
|  | Actual: | 1613.6
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 4 | Manager | Initialise repository |  | 2026-02-09 | 2026-02-09 00:10 | Completed | 0.17 | 0.17 | 8.5 | 8.5 | REQ 0 - Iniciar el repositorio del proyecto
2 | T0002/D | Development | Student 4 | Developer | Other (Describe) |  | 2026-02-09 16:00 | 2026-02-09 17:00 | Completed | 1 | 1 | 25 | 25 | REQ 0 - Personalizar el proyecto con los colores corporativos, banner…
3 | T0003/D | Development | Student 2 | Developer | Other (Describe) |  | 2026-02-16 16:00 | 2026-02-16 16:20 | Completed | 0.4 | 0.4 | 10 | 10 | REQ 0 - Crear 2 cuentas de administrador
4 | T0004/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-15 19:00 | 2026-02-15 20:36 | Completed | 1 | 1.6 | 25 | 40 | REQ C S1/1 - Implementar entidades
5 | T0005/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 12:00 | 2026-02-16 13:00 | Completed | 1 | 1 | 25 | 25 | REQ C S2/1 - Implementar entidades
6 | T0006/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-16 12:50 | 2026-02-16 14:20 | Completed | 1 | 1.5 | 25 | 37.5 | REQ C S3/1 - Implementar entidades
7 | T0007/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-16 12:00 | 2026-02-16 13:32 | Completed | 1 | 1.53 | 25 | 38.25 | REQ C S4/1 - Implementar entidades
8 | T0008/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-21 17:48 | 2026-02-21 18:07 | Completed | 0.5 | 0.33 | 12.5 | 8.25 | REQ 0 - Implementar ValidText
9 | T0009/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-19 18:03 | 2026-02-19 18:24 | Completed | 0.5 | 0.33 | 12.5 | 8.25 | REQ 0 - Implementar ValidTicker
10 | T0010/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-21 19:10 | 2026-02-21 19:27 | Completed | 0.5 | 0.28 | 12.5 | 7 | REQ 0 - Implementar ValidHeader
11 | T0011/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-28 12:30 | 2026-02-28 13:36 | Completed | 0.75 | 1 | 18.75 | 25 | REQ C S1/1 - Implementar entidades (restricción a nivel de clase)
12 | T0012/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-02 10:24 | 2026-03-02 11:10 | Completed | 0.75 | 0.75 | 18.75 | 18.75 | REQ C S3/1 - Implementar entidades (restricción a nivel de clase)
13 | T0013/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-01 11:03 | 2026-03-01 12:07 | Completed | 0.75 | 1 | 18.75 | 25 | REQ C S2/1 - Implementar entidades (restricción a nivel de clase)
14 | T0014/D | Development | Student 4 | Developer | Implement feature |  | 2026-01-30 18:00 | 2026-01-30 19:15 | Completed | 0.75 | 1.25 | 18.75 | 31.25 | REQ C S4/1 - Implementar entidades (restricción a nivel de clase)
15 | T0015/D | Development | Student 1 | Tester | Other (Describe) |  | 2026-03-02 11:00 | 2026-03-02 13:11 | Completed | 1.5 | 2.12 | 45 | 63.6 | REQ C S1/6 - Poblar base de datos
16 | T0016/D | Development | Student 2 | Tester | Other (Describe) |  | 2026-03-02 10:20 | 2026-03-02 13:29 | Completed | 1.5 | 3.15 | 45 | 94.5 | REQ C S2/6 - Poblar base de datos
17 | T0017/D | Development | Student 3 | Tester | Other (Describe) |  | 2026-03-02 11:15 | 2026-03-02 13:20 | Completed | 1.5 | 2.12 | 45 | 63.6 | REQ C S3/6 - Poblar base de datos
18 | T0018/D | Development | Student 4 | Tester | Other (Describe) |  | 2026-03-02 11:35 | 2026-03-02 13:40 | Completed | 1.5 | 2.08 | 45 | 62.4 | REQ C S4/6 - Poblar base de datos
19 | T0019/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-08 13:15 | 2026-03-08 16:41 | Completed | 3 | 3.43 | 75 | 85.75 | REQ C S1/2 - Listar invenciones
20 | T0020/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-08 10:32 | 2026-03-08 13:07 | Completed | 3 | 3.41 | 75 | 85.25 | REQ C S2/2 - Listar campañas
21 | T0021/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-08 10:30 | 2026-03-08 13:30 | Completed | 3 | 3 | 75 | 75 | REQ C S3/2 - Listar strategies
22 | T0022/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-08 09:20 | 2026-03-08 12:50 | Completed | 3 | 3.5 | 75 | 87.5 | REQ C S4/2 - Listar sponsorships
23 | T0023/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-14 15:30 | 2026-03-14 19:43 | Completed | 4 | 4.2 | 100 | 105 | REQ C S1/4- Crud de invention y parts + publicar invención.
24 | T0024/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-15 10:05 | 2026-03-15 13:30 | Completed | 4 | 3.41 | 100 | 85.25 | REQ C S2/4- Crud de campañas y milestones + publicar campaña
25 | T0025/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-15 21:48 | 2026-03-16 02:30 | Completed | 4 | 4.7 | 100 | 117.5 | REQ C S3/4- Crud de estrategias y milestones + publicar estrategias
26 | T0026/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-15 09:35 | 2026-03-15 13:29 | Completed | 4 | 3.9 | 100 | 97.5 | REQ C S4/4 - Crud de sponsorships y donaciones + publicar sponsorships
27 | T0027/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-16 11:00 | 2026-03-16 11:20 | Completed | 0.5 | 0.33 | 12.5 | 8.25 | REQ C S1/3 - Adquirir rol inventor y actualizar datos del rol
28 | T0028/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-16 11:05 | 2026-03-16 11:34 | Completed | 0.5 | 0.48 | 12.5 | 12 | REQ C S2/3 - Adquirir rol spokesperson y actualizar datos del rol
29 | T0029/R/ | Revision | Student 1 | Tester | Other (Describe) |  | 2026-03-16 15:30 | 2026-03-16 16:30 | Completed | 2 | 2 | 60 | 60 | Test informal de los requisitos revisión para preparar la entrega
30 | T0030/R/ | Revision | Student 2 | Tester | Other (Describe) |  | 2026-03-16 15:30 | 2026-03-16 16:30 | Completed | 2 | 2 | 60 | 60 | Test informal de los requisitos revisión para preparar la entrega
31 | T0031/R/ | Revision | Student 3 | Tester | Other (Describe) |  | 2026-03-16 15:30 | 2026-03-16 16:30 | Completed | 2 | 2 | 60 | 60 | Test informal de los requisitos revisión para preparar la entrega
32 | T0032/R/ | Revision | Student 4 | Tester | Other (Describe) |  | 2026-03-16 15:30 | 2026-03-16 16:30 | Completed | 2 | 2 | 60 | 60 | Test informal de los requisitos revisión para preparar la entrega
33 | T0033/R/ | Revision | Student 3 | Developer | Implement feature |  | 2026-03-17 10:00 | 2026-03-17 10:30 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | REQ C S3/3 - Adquirir rol fundraiser y actualizar datos del rol
34 | T0034/R/ | Revision | Student 4 | Developer | Implement feature |  | 2026-03-17 13:00 | 2026-03-17 13:25 | Completed | 0.5 | 0.41 | 12.5 | 10.25 | REQ C S4/3 - Adquirir rol sponsor y actualizar datos del rol
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 1801.575
|  | Actual: | 1848.15
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/D | Development | Student 1 | Tester | Test feature formally |  | 2026-04-13 12:00 | 2026-04-13 13:00 | Completed | 0.75 | 1 | 22.5 | 30 | Tests "legal" de Invention y Part
2 | T0002/M | Management | Student 2 | Manager | Other (Describe) |  | 2026-04-27 12:00 | 2026-04-27 12:43 | Completed | 0.5 | 0.71 | 25 | 35.5 | Redacción de requisitos del entregable B
3 | T0003/O | Other | Student 1 | Analyst | Create domain model |  | 2026-04-27 12:45 | 2026-04-27 13:25 | Completed | 0.5 | 0.66 | 20 | 26.4 | Realización del diagrama UML del modelo de dominio
4 | T0004/D | Development | Student 1 | Developer | Implement feature |  | 2026-04-29 12:00 | 2026-04-29 14:00 | Completed | 2 | 2 | 50 | 50 | Implementación de la clase Project, sus relaciones, su validador y sus datos de prueba
5 | T0005/D | Development | Student 1 | Developer | Implement feature |  | 2026-04-30 12:30 | 2026-04-30 14:41 | Completed | 1.5 | 2.18 | 37.5 | 54.5 | Implementación de las features show y list de Project y sus componentes
6 | T0006/D | Development | Student 2 | Developer | Implement feature |  | 2026-04-29 16:00 | 2026-04-29 17:00 | Completed | 1 | 1 | 25 | 37.5 | Implementación de Audit Report y todo lo relacionado con esta clase que era del student 5
7 | T0007/D | Development | Student 2 | Developer | Implement feature |  | 2026-04-29 17:00 | 2026-04-29 17:30 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Implementación de Member y MemberProject
8 | T0008/D | Development | Student 1 | Developer | Implement feature |  | 2026-04-29 17:00 | 2026-04-29 18:40 | Completed | 2.5 | 1.666 | 62.5 | 41.65 | Implementación de las features del rol Manager crear, editar, eliminar y publicar proyecto
9 | T0009/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-04 12:00 | 2026-05-04 13:20 | Completed | 2 | 2.333 | 50 | 58.325 | Implementación de las features del rol Manager de asignar Miembros al proyecto y listarlos
10 | T0010/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-04 16:00 | 2026-05-04 17:20 | Completed | 1.333 | 1.333 | 33.325 | 33.325 | Implementación de las features del rol Manager de asignar Miembros al proyecto y listarlos
11 | T0011/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-05 11:13 | 2026-05-05 13:20 | Completed | 2 | 2.11 | 50 | 52.75 | Implementación de las features del rol Manager de eliminar Miembros del proyecto
12 | T0012/D | Development | Student 2 | Developer | Implement feature |  | 2026-05-01 10:00 | 2026-05-01 13:00 | Completed | 2.5 | 3 | 62.5 | 75 | Implementación de list y show de Project y componentes de un Project para Member
13 | T0013/D | Development | Student 2 | Developer | Implement feature |  | 2026-05-04 16:20 | 2026-05-04 18:30 | Completed | 2 | 2.1 | 50 | 52.5 | Implementación de list y show de Inventor, Spokesperson y Fundraiser de un proyecto para Member
14 | T0014/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-05 15:35 | 2026-05-05 17:00 | Completed | 2 | 1.41 | 50 | 35.25 | Implementacion de list y show de Part, Mileston y Tactic para los proyectos (con rol manager) y archivos i18n de todo lo implementado hasta el momento
15 | T0015/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-06 11:15 | 2026-05-06 13:50 | Completed | 3 | 2.58 | 75 | 64.5 | Implementación de show y list de project para el rol any y realizados tests de algunas features de manager
16 | T0016/D | Development | Student 2 | Developer | Implement feature |  | 2026-05-05 16:00 | 2026-05-05 18:00 | Completed | 2 | 2 | 50 | 50 | Implementación de show y list de Part, Milestone y Tactic de los proyectos para Member. Y show de Manager de un proyecto para Member
17 | T0017/D | Development | Student 2 | Developer | Implement feature |  | 2026-05-05 18:30 | 2026-05-05 19:00 | Completed | 1 | 0.5 | 25 | 12.5 | Implementación de show de Spokesperson, Fundraiser e Inventor de un componente de un proyecto para Member
18 | T0018/D | Development | Student 2 | Developer | Implement feature |  | 2026-05-06 10:00 | 2026-05-06 16:00 | Completed | 3 | 4 | 75 | 100 | Implementación de asignar y desasignar componentes a un proyecto para Member
19 | T0019/D | Development | Student 1 | Tester | Test feature formally |  | 2026-05-06 17:00 | 2026-05-06 19:50 | Completed | 2.5 | 2.8 | 75 | 84 | Test legales de todas las features de manager
20 | T0020/D | Development | Student 1 | Tester | Test feature formally |  | 2026-05-07 11:30 | 2026-05-07 13:35 | Completed | 2.5 | 2.08 | 75 | 62.4 | Test de hacking de todas las features de manager
21 | T0021/D | Development | Student 2 | Tester | Test feature formally |  | 2026-05-06 17:00 | 2026-05-06 19:00 | Completed | 2 | 2 | 60 | 60 | Test legales de todas las features de member
22 | T0022/D | Development | Student 2 | Tester | Test feature formally |  | 2026-05-07 17:00 | 2026-05-07 19:00 | Completed | 2 | 2 | 60 | 60 | Test de hacking de todas las features de member
23 | T0023/O | Other | Student 1 | Analyst | Write report |  | 2026-05-07 17:40 | 2026-05-07 19:30 | Completed | 1 | 1.8 | 40 | 72 | Eliminación de malos olores y Lint Report
24 | T0024/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-08 11:00 | 2026-05-08 12:15 | Completed | 1.5 | 1.25 | 37.5 | 31.25 | Implementación de feature de Banner
25 | T0025/D | Development | Student 1 | Tester | Test feature formally |  | 2026-05-08 12:15 | 2026-05-08 13:25 | Completed | 0.5 | 1.16 | 15 | 34.8 | Repetir tests que dan error
26 | T0026/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-01 09:00 | 2026-05-01 10:00 | Completed | 0.8 | 1 | 20 | 25 | Implementación del list del dashboard del Manager
27 | T0027/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-01 10:00 | 2026-05-01 11:30 | Completed | 1.3 | 1.5 | 32.5 | 37.5 | Implementación del show del dashboard del Manager
28 | T0028/D | Development | Student 4 | Tester | Test feature formally |  | 2026-05-01 11:30 | 2026-05-01 13:00 | Completed | 1.6 | 1.5 | 48 | 45 | Testing legal e ilegal del list y show del dashboard
29 | T0029/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-02 09:00 | 2026-05-02 10:30 | Completed | 1.1 | 1.5 | 27.5 | 37.5 | Implementación de assign de audit report a un proyecto (Auditor)
30 | T0030/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-02 10:30 | 2026-05-02 11:30 | Completed | 0.9 | 1.2 | 22.5 | 30 | Implementación de unassign de audit report a un proyecto (Auditor)
31 | T0031/D | Development | Student 4 | Tester | Test feature formally |  | 2026-05-02 11:30 | 2026-05-02 12:30 | Completed | 1.4 | 1 | 42 | 30 | Testing de asignación y desasignación para Auditor
32 | T0032/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-03 09:00 | 2026-05-03 10:30 | Completed | 0.7 | 1.5 | 17.5 | 37.5 | Implementación de assign de patrocinio a un proyecto (Sponsor)
33 | T0033/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-03 10:30 | 2026-05-03 11:30 | Completed | 1.9 | 1 | 47.5 | 25 | Implementación de unassign de patrocinio a un proyecto (Sponsor)
34 | T0034/D | Development | Student 4 | Tester | Test feature formally |  | 2026-05-03 11:30 | 2026-05-03 12:30 | Completed | 1.2 | 1 | 36 | 30 | Testing de asignación y desasignación para Sponsor
35 | T0035/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-04 09:00 | 2026-05-04 10:00 | Completed | 0.6 | 1 | 15 | 25 | Implementación del list de invenciones en un proyecto (Auditor/Sponsor)
36 | T0036/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-04 10:00 | 2026-05-04 11:00 | Completed | 1.5 | 1 | 37.5 | 25 | Implementación del show de invenciones en un proyecto (Auditor/Sponsor)
37 | T0037/D | Development | Student 4 | Tester | Test feature formally |  | 2026-05-04 11:00 | 2026-05-04 12:00 | Completed | 1.1 | 1.1 | 33 | 33 | Testing de list y show de invenciones para Auditor y Sponsor
38 | T0038/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-05 09:00 | 2026-05-05 10:00 | Completed | 0.85 | 1 | 21.25 | 25 | Implementación del list de campañas en un proyecto (Auditor/Sponsor)
39 | T0039/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-05 10:00 | 2026-05-05 11:00 | Completed | 1.3 | 1 | 32.5 | 25 | Implementación del show de campañas en un proyecto (Auditor/Sponsor)
40 | T0040/D | Development | Student 4 | Tester | Test feature formally |  | 2026-05-05 11:00 | 2026-05-05 12:00 | Completed | 1.75 | 1 | 52.5 | 30 | Testing de list y show de campañas para Auditor y Sponsor
41 | T0041/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-08 09:00 | 2026-05-08 10:00 | Completed | 0.95 | 1 | 23.75 | 25 | Implementación del list de estrategias en un proyecto (Auditor/Sponsor)
42 | T0042/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-08 10:00 | 2026-05-08 11:00 | Completed | 1.25 | 1 | 31.25 | 25 | Implementación del show de estrategias en un proyecto (Auditor/Sponsor)
43 | T0043/D | Development | Student 4 | Tester | Test feature formally |  | 2026-05-08 11:00 | 2026-05-08 12:00 | Completed | 1.6 | 1.2 | 48 | 36 | Testing de list y show de estrategias para Auditor y Sponsor
44 | T0044/D | Revision | Student 2 | Tester | Write report |  | 2026-05-08 17:00 | 2026-05-08 18:30 | Completed | 1.5 | 1.5 | 45 | 45 | Testing report
45 | T0045/D | Revision | Student 2 | Tester | Write report |  | 2026-05-08 21:00 | 2026-05-08 21:30 | Completed | 0.5 | 0.5 | 15 | 15 | Analysis report
46 | T0046/R/ | Revision | Student 1 | Tester | Write report |  | 2026-05-08 21:00 | 2026-05-08 21:30 | Completed | 0.5 | 0.5 | 15 | 15 | Performance testing
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O